## Slide 1: CHAPTER FOUR PROJECT MONITORING AND EVALUATION
1
Kumneger T. MAU 2020

## Slide 2: 4.1. What is Monitoring and Evaluation?
2
Monitoring
Is the systematic collection and analysis of information to enable managers and key stakeholders to make informed decisions, maintain existing practices, policies and principles and improve the performance of their projects.
  It is the regular gathering, analyzing and reporting of information that needed for evaluation.
  It is either ongoing or periodic observation of a project’s implementation to ensure that inputs, activities, outputs, and external factors are proceeding according to plan.
  provides information to alert the stakeholders whether the results are being achieved or not.

## Slide 3: Cont…...
3
Evaluation
Is a selective and periodic exercise that attempts to objectively assess the overall progress and worth of a project.
It uses the information gathered through monitoring and other research activities .
Monitoring Vs Evaluation
Monitoring checks whether the project is on track while evaluation questions whether the project is on the right track.
Monitoring is concerned with the short-term performances of the project while evaluation looks more at long-term effects of project goals.

## Slide 4: Cont…...
4
Monitoring tends to underline little problems before they become big
ones while evaluation is a systematic examination of a project to determine its efficiency, effectiveness, impact, sustainability, and the relevance of its objectives.
Traditionally, evaluation has been the last step in the project life cycle and in the project development process.
However, it does not make sense to wait until the project is finished to ask the question “Did we do the right thing?” Indeed, you could evaluate the effectiveness at each stage of the project life cycle.

## Slide 5: 4.2. Why Monitoring and Evaluation?
5
M&E can help an organization to extract relevant information from past and ongoing activities that can be used as the basis for future planning.
A structured M&E approach makes information available to support the implementation of projects and which enhance project sustainability.
M&E can helps to strength project implementation and encourage useful partnerships with key stakeholders.
The main objectives of M&E are :
  Ensure informed decision-making
  Enhance organizational and development learning
  Assist in policy development and improvement

## Slide 6: Cont…...
6
Provide mechanisms for accountability
Promote partnership and knowledge transfer to key Stakeholders
Build capacity in M&E tools and techniques

## Slide 7: 4.3. Kinds of Monitoring and Evaluation?
7
Internal Project M&E
Is built for the design of a project and is undertaken by the team that is responsible for management and implementation of the project.
External Project M&E
Is carried out by an outside team, which is not directly responsible for the management or implementation of the project.
It assess the effectiveness of the internal M&E put in place by the project management team.
External monitoring can take place once the project has been completed, and/or during implementation of the project.

## Slide 8: Cont…...
8
External M&E is often required by donor agencies or government organizations , if for example, they need to know how their funds are being spent or if their policies are being adhered to.
Findings and recommendations of external monitoring are often documented in a review or evaluation report.
External M&E also monitors and evaluates internal M&E
Figure 4.1- Differences between internal & external M&E.docx

## Slide 9: 4.4. Monitoring Levels
9
Traditionally, M&E focused on assessing the inputs and activities of a project.
Project inputs, activities and risks are also important, however, as they all affect outputs. For example, if the budget (an input) is cut by 50%, this will obviously affect the outputs of the project and will need to be taken into account when conducting the M&E.
There are various monitoring levels in a project; thus are:
1) Input Monitoring
 It is the monitoring of the resources that are put into the project; these include budget, staff, skills, etc.

## Slide 10: Cont…...
10
Information on this type of monitoring comes mainly from management reports, progress reports and accounting.
For example, ways of measuring this can be the number of days consultants are is employed, or the amount of funds spent on training and equipment .
2) Activity Monitoring
It monitors what happens during the implementation of the project and whether those activities, which were planned, were carried out.
This information is often taken from the progress report.

## Slide 11: Cont…...
11
3) Output Monitoring
It is a level between activity and impact monitoring .
This type of monitoring assesses the result or output from project inputs and activities .
The measurements used for output monitoring will be those which show the immediate physical outputs and services from the project.
4) Impact Monitoring
Impact monitoring relates to the objectives of the project.
The aim of impact monitoring is to analyze whether the broader development objectives of the project have been met.
 It demonstrate changes that are fundamental and sustainable without continued project support.

## Slide 12: 4.5. Monitoring and Evaluation Procedures
12
M&E procedure sets out the steps in planning and implementing external M&E.
The M&E procedure must be customized to the specific needs of each project, taking into account the project objectives, inputs, outputs, activities, stakeholders and beneficiaries .
The M&E steps will vary from situation to situation . Seven key steps are listed in Figure below:
Figure 4.2- The M&E procedures.docx

## Slide 13: Cont…...
13
Step 1: Establish the Purpose and Scope of M&E
Specifying the purpose and scope of the M&E helps to clarify what can be expected of the M&E procedure, how comprehensive it should be and what resources and time will be needed to implement it .
When formulating the purpose of M&E, relevant stakeholders including the project management team, should be consulted or at least made aware of and understand the purpose of the M&E
For example, to verify that the development objective and outputs of the project have been achieved within the allocated budget, the scope of the M&E may be determined by asking some of the following questions:

## Slide 14: Cont…...
14
What is the purpose of M&E?
How much money is available for your M&E?
What type of information is required by project management donor agents or other stakeholders?
What is the level of M&E expertise available?
To what extent should local communities and other stakeholders, participate in the M&E procedure?

## Slide 15: Cont…...
15
Step 2: Identify Performance Questions and Indicators
1) Performance Questions
A performance question is used to focus on whether performing as planned and if not, why not.
Performance questions will be guided by the broader objective, the project outputs, as well as the M&E purpose.
a project is
development
 Once performance questions have been identified, it will be easier to decide what information is needed to evaluate the project.

## Slide 16: Cont…...
16
2) Indicators
Indicators are basically measurements that can be used to assess the performance of the project.
While performance questions help to decide what should be monitored and evaluated, indicators provide the actual measurements for M&E and determine what data needs to be gathered.
The project itself may have indicators by which it monitors it's own progress - these may be used for external M&E, if relevant .
Indicators might be either qualitative or quantitative .

## Slide 17: Cont…...
17
Quantitative data is factual while qualitative information is based on opinions and perceptions and thus may be subject to further interpretation
During M&E, one should aim to have both qualitative and quantitative indicators . Those, indicator should be:
  Relevant - The indicators should be directly linked to the project objectives/ outputs.
  Technically feasible - The indicators should be capable of being verified or measured and analyzed.
  Reliable - The indicators should be based on exact information's .

## Slide 18: Cont…...
18
Usable - People carrying out the M&E should be able to understand and use the information provided by the indicators to evaluate the project.
Participatory - Relevant stakeholders should be involved in the collection of information generated by the indicators, the analysis of the information and possible use of the information in the future.
Step 3: Establish M&E Functions, Assign Responsibilities and Financial Resources
 Establishing M&E functions and responsibilities at the beginning of the procedure can help to avoid major communication issues, conflicts of interest, duplication of tasks and wasted efforts.

## Slide 19: Cont…...
19
Organizing responsibilities means deciding which stakeholders will be involved and clarifying and assigning roles to these stakeholders as well as to funding organization officials, project management and any partner organizations .
Stakeholders may need to be trained in different aspects of the M&E procedure.
M&E will require financial resources in accordance with the type of project(s) that is being evaluated as well as the M&E purpose, performance questions and indicators .

## Slide 20: Cont…...
20
Among the items that should be included in M&E costs are:
  Staff salaries;
  Fees and expenses for consultants ;
Fees and expenses for M&E training ;
Fees and expenses for organizing participatory exercises.
M&E meetings and other
 Consultants can play an important role in enabling projects to fulfill its M&E responsibilities by providing specialist knowledge and expertise that may not be readily available in the organization .

## Slide 21: Cont…...
21
Step 4: Gather and Organize Data
Data gives life to M&E. However, selecting methods of data collection can be confusing, unless it is approached in a systematic fashion.
Instead, using multiple methods helps to validate M&E findings and provides a more balanced and holistic view of project progress and achievements.
The performance questions and indicators will provide guidance in deciding what data/information to gather and the methods to be used.
Data can either be primary or secondary.

## Slide 22: Cont…...
22
Data Sources and Data Collection Methods
Potential data sources and data collection methods are listed below:
  Document Review: .
  Interviews :
  Surveys and Questionnaires :
  Field Visits and Transect Walks
  Expert Opinion Obtaining the views of experts who are knowledgeable about particular aspects of the project's.

## Slide 23: Cont…...
23
Organizing and Storing Data
Data needs to be captured, organized and stored so that it can be readily used for the M&E purposes.
Proper capturing, organizing and storage is particularly important when information has been collected from different sources with different methods.
Step 5: Analyze Data and Prepare an Evaluation Report
The captured and organized data needs to be analyzed, and findings and recommendations summarized and compiled into a report.

## Slide 24: Cont…...
24
In this regard, the performance questions and indicators can provide important assessment tools for the analysis.
A final comparison with the outputs and impacts of the project should then be made.
In this way performance, progress and achievements of the project can be assessed.
Reporting
Feedback and reporting are key to both internal and external M&E as, in this way, information can be meaningfully combined, explained, compared and presented.

## Slide 25: Cont…...
25
All reporting should thus be as accurate and relevant as possible.
As mentioned earlier, external M&E will frequently use the internal project progress reports and other relevant information as part of the information gathered to externally monitor and evaluate the project.
For external M&E the report is usually called an evaluation or review report.
Step 6: Disseminate Findings and Recommendations
The evaluation reports, or summaries of these reports, should be widely distributed and presented to decision-makers and key stakeholders - including those who were consulted in the M&E process.

## Slide 26: Cont…...
26
Step 7: Learn from the M&E
M&E provides information and facts that, when analyzed, understood and accepted, become knowledge that can be used to improve Project management .
Besides learning about the progress/achievements of the project outputs,
etc, it is essential strategies, project
to learn from what works regarding partnership design and implementation, and to feed this
knowledge back into ongoing and future projects and policies
 This information also provides a means to regulate the sustainable management of state projects by other agencies.

## Slide 27: Cont…...
27
 Project evaluations can help to bring development partners together, and when this occurs the learning from M&E goes beyond project to stakeholders involved in other development and natural resource management activities .